## Instructions
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
Instructions
1 | List the team members name above the block
2 | Title is a place to give a 1-3 word descritpion of the task for quick reference
3 | Description is a more detailed descrition of the task and should include acceptance critieria for the reviewer
4 | Initial Est is the expected number of hours needed to complete the task
5 | Change is to adjust your estimate. Use negative numbers if it took less time. Use Postitve values if it took more time.
6 | Completed is how many hours you have spent on the task.
7 | Testing is the date when you started testing your own code
8 | To Review is the date you deemed it complete and submitted it for review
9 | Submitted is the date when you finished making the adjustments suggested by the review and uploaded it to the collective group code.
10 | Reviewer is the person who completes the task review. Note this should happen even if there is no code.
11 | Code is where the file that your data can be found. This might be a text document if you were doing a non-coding tasking.
12 | TestCases is where the file that your test case can be found. This box may be blank if there was no implementation for this task.

## Burn Down Charts
SPRINT 0 | Total Hours
Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Hours Left | 48 | 48 | 48 | 45 | 37 | 37 | 37 | 17 | 17 | 12 | 8 | -7 | -7 | -7 | -13
Member 1 | 12
Member 2 | 12 | 2: 3
Member 3 | 12 | 3: 8; 6: 20; 8: 5
Member 4 | 12 | 9: 4; 10: 15; 13: 6
Member 5
Member 6
SPRINT 1 | Total Hours
Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Hours Left | 48 | 48 | 48 | 45 | 41 | 41 | 38 | 35 | 31 | 27 | 21 | 17 | 17 | 13 | 10
Member 1 | 12 | 2: 3; 3: 2; 7: 4
Member 2 | 12 | 3: 2; 5: 3; 6: 3
Member 3 | 12 | 8: 2; 9: 3; 10: 2; 12: 4
Member 4 | 12 | 8: 2; 9: 3; 10: 2; 13: 3
Member 5
Member 6
SPRINT 2 | Total Hours
Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Hours Left | 72 | 72 | 66 | 66 | 66 | 63 | 63 | 59 | 57 | 52 | 52 | 52 | 52 | 52 | 45 | 39 | 39 | 31 | 31 | 31 | 30 | 24
Member 1 | 18 | 1: 2; 4: 2; 8: 2; 13: 1; 16: 3; 19: 1
Member 2 | 18 | 1: 2; 6: 2; 7: 2; 8: 1; 13: 2; 16: 3; 20: 2
Member 3 | 18 | 1: 1; 4: 1; 6: 1; 8: 2; 13: 2; 14: 3; 16: 2; 20: 2
Member 4 | 18 | 1: 1; 6: 1; 13: 2; 14: 3; 20: 2
Member 5
Member 6
SPRINT 3 | Total Hours | bar: 1 to 14
Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Hours Left | 48 | 48 | 39 | 35 | 24 | 20 | 10 | 10 | 1 | -3 | -6 | -9 | -13 | -16 | -20
Member 1 | 12 | 3 |  | 3 | 2 | 4 |  | 3 | 2 | 1 |  | 2 | 1
Member 2 | 12 | 3: 2; 4: 2; 5: 2; 7: 3; 9: 1; 11: 2; 12: 1
Member 3 | 12 | 1: 3; 3: 3; 5: 1; 7: 3; 8: 2; 13: 2
Member 4 | 12 | 1: 3; 2: 4; 3: 3; 5: 3; 9: 1; 10: 3; 12: 1; 13: 2
Member 5
Member 6
SPRINT 4 | Total Hours
Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Hours Left | 72 | 72 | 64 | 60 | 54 | 49 | 43 | 40 | 33 | 25 | 25 | 17 | 15 | 9 | 7
Member 1 | 12 | 1: 2; 4: 3; 6: 3; 7: 2; 10: 2
Member 2 | 12 | 1: 2; 4: 2; 7: 2; 10: 3; 11: 2
Member 3 | 12 | 1: 2; 3: 3; 5: 2; 8: 4; 12: 2; 13: 2
Member 4 | 12 | 1: 2; 2: 4; 3: 3; 5: 4; 7: 3; 8: 4; 10: 3; 12: 4
Member 5 | 12
Member 6 | 12

## Sprint 0
TEAM MEMBER: |  | Kevin Ramirez
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Product Design | Learn about the major itself given the links provided by the sponsor | 3 | -1 | 2 | Jan 31st | Feb 1st | Jan 31st | O'Brien | None
2 | Database Framework | Create the framework design for the main database for all projected info | 3 | -1 | 2 | Jan 31st | Feb 1st | Jan 31st | O'Brien | None
3
4
5
6
7
8
9
10
TEAM MEMBER: |  | Cooper Jordan
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Product Design | Learn about the major itself given the links provided by the sponsor | 3 | -1 | 2 | Jan 31st | Feb 1st | Jan 31st | O'Brien | None
2 | Database Framework | Create the framework design for the main database for all projected info | 3 | -1 | 2 | Jan 31st | Feb 1st | Jan 31st | O'Brien | None
3
4
5
6
7
8
9
10
TEAM MEMBER: |  | Anthony Lopez
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Product Design | Learn the major pathway of Product Design | 3 | -1 | 2 | Jan 31st | Feb 1st | Jan 31st | O'Brien | None
2 | Graphic Design | Decide on the graphic design choices for the site | 3 | -1 | 2 | Jan 31st | Feb 1st | Jan 31st | O'Brien | None
3
4
5
6
7
8
9
10
TEAM MEMBER: |  | Julian Bottero
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Product Design | Learn the major itself given the links provided by the sponsor | 3 | -1 | 2 | Jan 31st | Feb 1st | Jan 31st | O'Brien | None
2 | Graphic Design | Decide on the pathway layout for different sites | 3 | -1 | 2 | Jan 31st | Feb 1st | Jan 31st | O'Brien | None
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10

## Sprint 1
TEAM MEMBER: |  | Kevin Ramirez
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Database Outline | Implement the foundations for the database | 3 | 2 | Yes | Feb 9th | Feb 10th | Feb 9th | O'Brien | None
2 | Merge Framework | Design a framework for the backend-frontend communication | 3 | 1 | No | Feb 9th | Feb 10th | Feb 9th | O'Brien | None
3
4
5
6
7
8
9
10
TEAM MEMBER: |  | Cooper Jordan
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Database Outline | Implement the foundations for the database | 3 | 2 | Yes | Feb 9th | Feb 10th | Feb 9th | O'Brien | None
2 | Merge Framework | Design a framework for the backend-frontend communication | 3 | 1 | No | Feb 9th | Feb 10th | Feb 9th | O'Brien | None
3
4
5
6
7
8
9
10
TEAM MEMBER: |  | Anthony Lopez
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Website Outline | Implement the foundations for the website | 3 | 0 | Yes | Feb 9th | Feb 10th | Feb 9th | O'Brien | None
2 | Website Style | Decide on a CSS framework | 3 | 1 | No | Feb 9th | Feb 10th | Feb 9th | O'Brien | None
3
4
5
6
7
8
9
10
TEAM MEMBER: |  | Julian Bottero
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Website Outline | Implement the foundations for the website | 3 | 0 | Yes | Feb 9th | Feb 10th | Feb 9th | O'Brien | None
2 | Website Style | Decide on a CSS framework | 3 | 1 | No | Feb 9th | Feb 10th | Feb 9th | O'Brien | None
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10

## Sprint 2
TEAM MEMBER: |  | Kevin Ramirez
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Database Creation | Create the database for information storage using the created ERD | 6 | -4 | No |  | Feb 25th |  | O'Brien
2 | Merger Framework | Further work on the pathways for backend-frontend communication | 3 | -2 | No |  | Feb 25th |  | O'Brien
3 | Information Integration | Ensure all information is loaded and accessible from the database | 3 | -3 | Yes |  | Feb 25th |  | O'Brien
4 | Demonstration for sponsor | Initialize presentation that demonstrates our project to sponsor | 2 | -2 | Yes |  | Feb 25th
5
6
7
8
9
10
TEAM MEMBER: |  | Cooper Jordan
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Database Design | Design way that data can be connected and accessed | 6 | -6 | Yes |  | Feb 25th |  | O'Brien
2 | Merge Framework | Further work on the pathways for backend-frontend communication | 3 | -2 | No |  | Feb 25th |  | O'Brien
3 | Connect Database | Connect data tables in database | 5 | -4 | No |  | Feb 25th |  | O'Brien
4 | Information Integration | Ensure all information is loaded and accessible from the database | 3 | -2 | Yes |  | Feb 25th
5
6
7
8
9
10
TEAM MEMBER: |  | Anthony Lopez
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Login Page | Finalize work on the student login page and work on separate admin pages | 3 | -2 | No |  | Feb 25th |  | O'Brien
2 | Menu Page | Start the foundations of the menu page | 5 | -5 | Yes |  | Feb 25th |  | O'Brien
3 | First Assessment UI design | Design a prototype UI for a fill-in-the-blank assessment | 3 | -3 | No |  | Feb 25th |  | O'Brien
4 | Manage Permissions | Decide on what permissions students versus admins should have | 2 | -2 | No |  | Feb 25th
5 | First Assessment UI page | initialize HTML page for prototype UI; synergize UI prototype with HTML | 2 | -2 | No |  | Feb 25th
6
7
8
9
10
TEAM MEMBER: |  | Julian Bottero
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Login Page | Finalize work on the student login page and work on separate admin pages | 3 | -4 | No |  | Feb 25th |  | O'Brien
2 | Menu Page | Start the foundations of the menu page | 5 | -4 | Yes |  | Feb 25th |  | O'Brien
3 | Manage permissions | decide on what permissions students versus administrators should have | 2 | -1 | No |  | Feb 25th |  | O'Brien
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10

## Sprint 3
| TEAM MEMBER: |  | Kevin Ramirez
| TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
| Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
| 1 | Design Content Table | Draw up table for database to store/organize Product Design data | 2 | 0 | 2 | Mar 28th | Apr 1st | Mar 31st | O' Brien
| 2 | Organize Content | Organize PD content into content table | 3 | -1 | 2 | Mar 28th | Apr 1st | Mar 31st | O' Brien
| 3 | record SQL queries | Record queries made to insert and organize content from table | 2 | -1 | 1 | N/A | Apr 1st | Mar 31st | O' Brien
| 4 | Micro. Azure hosting | set up a microsoft azure server to host database publically (w/ Cooper) | 3 | 2 | 5 | Mar 28th | Apr 1st | Mar 31st | O' Brien
5
6
7
8
9
10
| TEAM MEMBER: |  | Cooper Jordan
| TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
| Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
| 1 | Micro. Azure hosting | Help set up a microsoft azure server to host database publically (w/ Kevin) | 3 | 2 | 5 | Mar 28th | Apr 1st | Mar 31st | O' Brien
| 2 | Design User info table | Create table for storing user login data (passwords, usernames). | 2 | -1 | 1 | Mar 28th | Apr 1st | Mar 31st | O' Brien
| 3 | Revise login queries | Revise Julian's sql code for storing user information | 2 | 0 | 2 | Mar 28th | Apr 1st | Mar 31st | O' Brien
| 4 | record SQL queries | Record queries made to insert/extract user login information | 2 | -1 | 1 | N/A | Apr 1st | Mar 31st | O' Brien
5
0
7
8
9
10
| TEAM MEMBER: |  | Anthony Lopez
| TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
| Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
| 1 | Create Nav template | Create the Navigation tab through HTML and Bootstrap | 3 | -1 | 2 | Mar 28th | Apr 1st | Mar 31st | O' Brien
] | 2 | Design Flash Card | Allocate/decide what information will be on the flash cards for games | 1 | 1 | 2 | N/A | Apr 1st | Mar 31st | O' Brien
| 3 | Flash card game mockup | Display card on a webpage design, mockup of the game page | 3 | -2 | 1 | Mar 28th | Apr 1st | Mar 31st | O' Brien
| 4 | Content Table Categories | Provide categories for the content table from Product Design Resources | 2 | 0 | 2 | Mar 28th | Apr 1st | Mar 31st | O' Brien
| 5 | Design Logo for app | Provide basic stand in logo | 1 | 0 | 1 | N/A | Apr 1st | Mar 31st | O' Brien
6
7
8
9
10
| TEAM MEMBER: |  | Julian Bottero
| TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
| Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
| 1 | Account making | Allow users to make accounts for login details | 3 | 1 | 4 | Mar 28th | Apr 1st | Mar 31st | O' Brien
| 2 | homepage widgets | Decide what options the user will have after the login screen | 2 | -1 | 1 | Mar 28th | Apr 1st | Mar 31st | O' Brien
| 3 | User login data storage | develop queries to store information into the database | 3 | 1 | 4 | Mar 28th | Apr 1st | Mar 31st | O' Brien
| 4 | Admin Option | Create check for users to login as an admin or a student | 2 | 0 | 2 | Mar 28th | Apr 1st | Mar 31st | O' Brien
| 5 | User login data extraction | Develop queries to extract information from the database into the app | 2 | 0 | 2 | Mar 28th | Apr 1st | Mar 31st | O' Brien
6
7
8
9
10
TEAM MEMBER:
| TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
| Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
| TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
| Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10

## Sprint 4
TEAM MEMBER: |  | Kevin Ramirez
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Extraction Queries | Create sql queries to pull data from database to assessments | 3 | -1 | 2 | N/A | 2024-04-12 | N/A | O' Brien | N/A | N/A
2 | Sample data Set | Create test that pulls a product, their designer, location, etc. | 3 | 0 | 3 | 2024-04-13 | 2024-04-13 | 2024-04-15 | Anthony L. | Github | N/A
3 | student account management | Give admins access to add or remove students from classes | 3 | 1 | 4 | 2024-04-10 | 2024-04-10 | 2024-04-15 | Julian B. | Github | Github
4 | Connecting database | replace test database with current sample/complete database | 2 | 1 | 3 | 2024-04-13 | 2024-04-13 | 2024-04-15 | Anthony L. | Github | GitHub
5
6
7
8
9
10
TEAM MEMBER: |  | Cooper Jordan
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Already user check | For users who have already created an account, call a check to prevent duplicate accounts | 3 | -1 | 2 | 2024-04-12 | 2024-04-12 | 2024-04-12 | Julian B. | Github | GitHub
2 | Student account management | Give admins access to add or remove students from classes | 3 | 1 | 4 | 2024-04-10 | 2024-04-10 | 2024-04-15 | Julian B | Github | GitHub
3 | Connecting Database | replace test database with current sample/complete database | 2 | 1 | 3 | 2024-04-13 | 2024-04-13 | 2024-04-15 | Anthony L. | Github | Github
4
5
6
7
8
9
10
TEAM MEMBER: |  | Anthony Lopez
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Classes page | page for managing classes with widget links for different classes and students | 3 | 2 | 5 | 2024-04-10 | 2024-04-12 | 2024-04-12 | Julian B. | Github | Github
2 | Assessments page | page for accessing learning assessments, with links to the flash card game and other assessments. | 3 | 2 | 5 | 2024-04-13 | 2024-04-13 | 2024-04-13 | Julian B. | Github | Github
3 | Sidebar Nav Menu | Finish the Navigation menu for the web app with hyperlinks | 2 | 0 | 2 | 2024-04-06 | 2024-04-09 | 2024-04-09 | Julian B. | Github | Github
4 | Design Widgets Box | Create design for widget boxes to click | 2 | -1 | 1 | N/A | 2024-04-09 | 2024-04-09 | Julian B. | N/A | N/A
5 | Website Mockups | Create some mockups for the website for what it should look like at the end | 2 | 0 | 2 | N/A | 2024-04-09 | 2024-04-09 | Julian B. | N/A | N/A
6
7
8
9
10
TEAM MEMBER: |  | Julian Bottero
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1 | Student homepage | homepage widgets and assessments for student view | 3 | 2 | 5 | 2024-04-06 | 2024-04-10 | 2024-04-15 | Anthony L. | Github | N/A
2 | Admin homepage | homepage widgets and assessments for admin view | 3 | 2 | 5 | 2024-04-06 | 2024-04-10 | 2024-04-15 | Anthony L. | Github | N/A
3 | Sidebar Nav Menu | Finish Navigation menu for the web app with hyperlinks | 2 | 1 | 3 | 2024-04-06 | 2024-04-09 | 2024-04-09 | Anthony L. | Github | N/A
4 | Setup Web Server | Setting up web server to host site | 3 | 0 | 3 | 2024-04-11 | 2024-04-12 | 2024-04-13 | Anthony L. | Github | N/A
5 | Connecting Database | replace test database with current sample/complete database | 2 | 1 | 3 | 2024-04-13 | 2024-04-13 | 2024-04-15 | Anthony L. | Github | GitHub
6 | Card Game Build #1 | come up with a basic build to display the card and some options | 4 | 2 | 6 | 2024-04-13 | 2024-04-13 | 2024-04-13 | Julian B. | Github | GitHub
7 | Demo preperation | Prepare a demo to present to the class / Sponsor | 2 | 0 | 2 | N/A | 2024-04-15 | 2024-04-15 | Anthony L. | N/A | N/A
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10
TEAM MEMBER:
TASK |  |  | HOURS |  |  | DATES |  |  | REVIEWER | FILES
Task | Title | Descrition | Initial Est | Change | Completed | Testing | to Reviewer | Submitted | Reviewer | Code | Test Cases
1
2
3
4
5
6
7
8
9
10